## Sheet1
Requirement | What was delivered | Implementation decision | Evidence
R-001 | Historical traffic-event storage | Persist events after they disappear from the live source | Database / sample historical records
R-002 | Automated data collection | Scheduled collection from QLD Traffic source | Repository / running deployment
R-003 | Event vs observation handling | Use source event identifiers to prevent repeated observations being counted as new events | Database records / query result
R-004 | Snapshot export and analysis notebook | Export the database to CSV, analyse it in Python and publish the results as a report | https://traffic.jcdelgado.dev/report
R-005 | Public analytical interface | Selected metrics exposed through the website | https://traffic.jcdelgado.dev
R-006 | Time since latest crash | Show the latest crash's start time in Brisbane time and the time elapsed since | https://traffic.jcdelgado.dev
R-007 | Analysis-ready data | Store records in structured fields suitable for querying/dataframes | Database/query example
R-008 | Not implemented | Deferred: low value relative to effort at project close. The worker logs failed polls and retries, but nothing is stored | None